## worklogs
Author | Summary | Work description | Issue | Parent | Epic | Started | Assignee | Labels | Priority | Resolution | Reporter | Status | Issue Type | Time spent
Sudikshya Bhattarai | Send code to team 6 for deployment and help |  | PSP2-65 | PSP2-61 | _ | Dec 13, 2023, 7:20 PM | Sudikshya Bhattarai | _ | Medium | _ | Anmol Arora | Review | Subtask | 4h
Toan Le Tran | Git readme is updated to have all installation instructions |  | PSP2-62 | PSP2-61 | _ | Dec 13, 2023, 6:56 PM | Toan Le Tran | _ | Medium | _ | Anmol Arora | To Do | Subtask | 2h 30m
Anmol Arora | MIT License added to repo | mit license added | PSP2-60 | _ | _ | Dec 13, 2023, 10:09 AM | Anmol Arora | git | Medium | Done | Anmol Arora | Done | Task | 1h
Sviatoslav Vasev | Make C4 diagram |  | PSP2-58 | _ | _ | Dec 7, 2023, 11:30 PM | Sviatoslav Vasev | _ | Medium | Done | Sviatoslav Vasev | Done | Task | 2h
Anmol Arora | Sprint review slides |  | PSP2-57 | _ | _ | Dec 7, 2023, 9:59 PM | Anmol Arora | docs | Medium | _ | Anmol Arora | To Do | Task | 2h
Anmol Arora | Add documentation full structure to confluence |  | PSP2-56 | PSP2-8 | _ | Dec 7, 2023, 9:57 PM | Jennifer Hensley | docs | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Add documentation full structure to confluence |  | PSP2-56 | PSP2-8 | _ | Dec 8, 2023, 12:30 PM | Jennifer Hensley | docs | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Add documentation full structure to confluence |  | PSP2-56 | PSP2-8 | _ | Dec 8, 2023, 2:40 PM | Jennifer Hensley | docs | Medium | Done | Anmol Arora | Done | Task | 1h
Jennifer Hensley | Confluence Catchup Landing Page |  | PSP2-54 | _ | _ | Dec 8, 2023, 2:00 PM | Jennifer Hensley | docs | Medium | Done | Anmol Arora | Done | Task | 30m
Sviatoslav Vasev | Make OOP models |  | PSP2-52 | PSP2-8 | _ | Nov 23, 2023, 7:51 PM | Sviatoslav Vasev | bot,data | Medium | Done | Sviatoslav Vasev | Done | Task | 3h
Sviatoslav Vasev | Make OOP models | Add class diagram | PSP2-52 | PSP2-8 | _ | Nov 24, 2023, 12:26 PM | Sviatoslav Vasev | bot,data | Medium | Done | Sviatoslav Vasev | Done | Task | 30m
Anmol Arora | Fix Broken main branch | fix git | PSP2-51 | PSP2-8 | _ | Nov 22, 2023, 9:16 PM | Anmol Arora | git | Medium | Done | Jennifer Hensley | Done | Task | 2h
Anmol Arora | Create slide set for weekly demo | Started slides | PSP2-50 | PSP2-8 | _ | Nov 22, 2023, 9:17 AM | Anmol Arora | docs | Medium | Done | Anmol Arora | Done | Task | 1h
Anmol Arora | Create slide set for weekly demo | slide set | PSP2-50 | PSP2-8 | _ | Nov 23, 2023, 3:06 PM | Anmol Arora | docs | Medium | Done | Anmol Arora | Done | Task | 2h
Sviatoslav Vasev | Create slide set for weekly demo |  | PSP2-50 | PSP2-8 | _ | Nov 24, 2023, 1:00 PM | Anmol Arora | docs | Medium | Done | Anmol Arora | Done | Task | 30m
Anmol Arora | Add common user to db | added user to db | PSP2-49 | PSP2-8 | _ | Nov 17, 2023, 10:08 AM | Anmol Arora | _ | Medium | Done | Sviatoslav Vasev | Done | Task | 2h
Anmol Arora | Review Code and tickets |  | PSP2-48 | _ | _ | Nov 10, 2023, 1:04 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 3h
Anmol Arora | Review Code and tickets | reviewed backend timestamp code, unit test and oop models | PSP2-48 | _ | _ | Nov 24, 2023, 12:38 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 2h
Anmol Arora | Review Code and tickets | review completed | PSP2-48 | _ | _ | Dec 15, 2023, 12:10 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Gitlab yml file for CI |  | PSP2-47 | PSP2-8 | _ | Nov 17, 2023, 10:42 AM | Anmol Arora | ci/cd | Medium | _ | Anmol Arora | INVALID | Task | 2h
Sviatoslav Vasev | Save new users to db |  | PSP2-46 | PSP2-8 | _ | Nov 24, 2023, 4:00 PM | Sviatoslav Vasev | bot,data | Medium | Done | Sviatoslav Vasev | Done | Task | 3h
Sviatoslav Vasev | Save new users to db |  | PSP2-46 | PSP2-8 | _ | Dec 15, 2023, 11:37 AM | Sviatoslav Vasev | bot,data | Medium | Done | Sviatoslav Vasev | Done | Task | 1h
Sudikshya Bhattarai | Add a duplicate check to jobteaser_data.py |  | PSP2-45 | PSP2-8 | _ | Nov 24, 2023, 2:43 AM | Sudikshya Bhattarai | data | Medium | Done | Ozan Topcu | Done | Task | 6h
Sudikshya Bhattarai | Add a duplicate check to jobteaser_data.py |  | PSP2-45 | PSP2-8 | _ | Dec 8, 2023, 2:13 PM | Sudikshya Bhattarai | data | Medium | Done | Ozan Topcu | Done | Task | 1h
Ozan Topcu | Add a time stamp column for the job_ads table and set a rule to remove obselete ads |  | PSP2-44 | PSP2-8 | _ | Nov 20, 2023, 6:54 PM | Ozan Topcu | data | Medium | Done | Ozan Topcu | Done | Task | 10h
Jennifer Hensley | Create a job listing page for the bot |  | PSP2-43 | PSP2-8 | _ | Nov 15, 2023, 9:06 AM | Jennifer Hensley | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 1h 30m
Jennifer Hensley | Create a job listing page for the bot |  | PSP2-43 | PSP2-8 | _ | Nov 17, 2023, 2:50 PM | Jennifer Hensley | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 1h
Sviatoslav Vasev | Create a job listing page for the bot | Review and testing | PSP2-43 | PSP2-8 | _ | Nov 22, 2023, 5:30 PM | Jennifer Hensley | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 1h 30m
Sviatoslav Vasev | Create a job listing page for the bot | Review and fixes | PSP2-43 | PSP2-8 | _ | Nov 23, 2023, 5:56 PM | Jennifer Hensley | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 2h
Jennifer Hensley | Create a job listing page for the bot |  | PSP2-43 | PSP2-8 | _ | Nov 24, 2023, 10:48 AM | Jennifer Hensley | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 4h
Sviatoslav Vasev | Create start page for the bot |  | PSP2-42 | PSP2-8 | _ | Nov 3, 2023, 3:30 PM | Sviatoslav Vasev | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 1h
Sviatoslav Vasev | Create start page for the bot |  | PSP2-42 | PSP2-8 | _ | Nov 9, 2023, 9:00 PM | Sviatoslav Vasev | bot | Medium | Done | Sviatoslav Vasev | Done | Task | 3h
Sudikshya Bhattarai | Add ssh info to confluence | Added SSH info to confluence. | PSP2-41 | PSP2-8 | _ | Nov 3, 2023, 3:15 PM | Sudikshya Bhattarai | vm | Medium | Done | Anmol Arora | Done | Task | 25m
Toan Le Tran | Credentials should not be clear text |  | PSP2-39 | PSP2-8 | _ | Nov 7, 2023, 5:48 PM | Toan Le Tran | testing | Medium | Done | Anmol Arora | Done | Task | 45m
Toan Le Tran | Add unit test |  | PSP2-38 | PSP2-8 | _ | Nov 17, 2023, 1:46 PM | Toan Le Tran | ci/cd | Medium | Done | Anmol Arora | Done | Task | 2h
Toan Le Tran | Add unit test |  | PSP2-38 | PSP2-8 | _ | Nov 24, 2023, 4:33 AM | Toan Le Tran | ci/cd | Medium | Done | Anmol Arora | Done | Task | 10h
Ozan Topcu | Database install and api call in VM |  | PSP2-37 | PSP2-8 | _ | Nov 3, 2023, 8:38 PM | Ozan Topcu | data | Medium | Done | Anmol Arora | Done | Task | 1h
Ozan Topcu | Database install and api call in VM |  | PSP2-37 | PSP2-8 | _ | Nov 3, 2023, 7:56 PM | Ozan Topcu | data | Medium | Done | Anmol Arora | Done | Task | 6h
Ozan Topcu | Database install and api call in VM |  | PSP2-37 | PSP2-8 | _ | Nov 10, 2023, 12:36 PM | Ozan Topcu | data | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Switch to key-pair login |  | PSP2-34 | PSP2-31 | _ | Nov 3, 2023, 2:23 PM | Jennifer Hensley | _ | Medium | Done | Sviatoslav Vasev | Done | Subtask | 30m
Sviatoslav Vasev | Switch to key-pair login |  | PSP2-32 | PSP2-31 | _ | Oct 28, 2023, 7:59 PM | Sviatoslav Vasev | vm | Medium | Done | Sviatoslav Vasev | Done | Subtask | 30m
Anmol Arora | Enable SSH on New Pouta VM | created users and enabled login | PSP2-29 | PSP2-10 | _ | Oct 28, 2023, 4:08 PM | Anmol Arora | vm | Medium | Done | Anmol Arora | Done | Task | 1h
Anmol Arora | Enable SSH on New Pouta VM |  | PSP2-29 | PSP2-10 | _ | Nov 3, 2023, 2:13 PM | Anmol Arora | vm | Medium | Done | Anmol Arora | Done | Task | 1h
Anmol Arora | Enable SSH on New Pouta VM |  | PSP2-29 | PSP2-10 | _ | Nov 10, 2023, 3:02 PM | Anmol Arora | vm | Medium | Done | Anmol Arora | Done | Task | 1h
Jennifer Hensley | Documenation import from Software Requirements |  | PSP2-28 | PSP2-10 | _ | Oct 13, 2023, 2:59 PM | Jennifer Hensley | docs | Medium | Done | Anmol Arora | Done | Task | 45m
Sviatoslav Vasev | Database schema for jobs ads |  | PSP2-27 | PSP2-10 | _ | Oct 8, 2023, 4:00 PM | Sviatoslav Vasev | data | Medium | Done | Anmol Arora | Done | Task | 40m
Sviatoslav Vasev | Database schema for jobs ads |  | PSP2-27 | PSP2-10 | _ | Oct 13, 2023, 3:00 PM | Sviatoslav Vasev | data | Medium | Done | Anmol Arora | Done | Task | 20m
Ozan Topcu | Local Telegram bot, simple Hello World |  | PSP2-25 | PSP2-10 | _ | Oct 27, 2023, 3:53 PM | Ozan Topcu | frontend | Medium | Done | Anmol Arora | Done | Task | 1h
Ozan Topcu | Local Telegram bot, simple Hello World |  | PSP2-25 | PSP2-10 | _ | Nov 3, 2023, 12:42 PM | Ozan Topcu | frontend | Medium | Done | Anmol Arora | Done | Task | 2h
Sviatoslav Vasev | Figma Design for telegram bot UI |  | PSP2-24 | PSP2-10 | _ | Oct 8, 2023, 5:00 PM | Jennifer Hensley | frontend | Medium | Done | Anmol Arora | Done | Task | 30m
Sudikshya Bhattarai | Figma Design for telegram bot UI |  | PSP2-24 | PSP2-10 | _ | Oct 13, 2023, 12:53 PM | Jennifer Hensley | frontend | Medium | Done | Anmol Arora | Done | Task | 1h
Jennifer Hensley | Figma Design for telegram bot UI |  | PSP2-24 | PSP2-10 | _ | Oct 31, 2023, 8:47 AM | Jennifer Hensley | frontend | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Figma Design for telegram bot UI |  | PSP2-24 | PSP2-10 | _ | Oct 31, 2023, 11:23 AM | Jennifer Hensley | frontend | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Figma Design for telegram bot UI |  | PSP2-24 | PSP2-10 | _ | Nov 3, 2023, 12:54 PM | Jennifer Hensley | frontend | Medium | Done | Anmol Arora | Done | Task | 2h
Anmol Arora | WorkFlow update - Definition of Done and Acceptance Criteria |  | PSP2-23 | PSP2-10 | _ | Oct 6, 2023, 2:19 PM | Anmol Arora | docs | Medium | Done | Anmol Arora | Done | Task | 30m
Anmol Arora | WorkFlow update - Definition of Done and Acceptance Criteria |  | PSP2-23 | PSP2-10 | _ | Nov 10, 2023, 2:02 PM | Anmol Arora | docs | Medium | Done | Anmol Arora | Done | Task | 2h
Toan Le Tran | Mock setup gitlab CI/CD with testing method |  | PSP2-22 | PSP2-10 | _ | Oct 27, 2023, 12:19 PM | Toan Le Tran | ci/cd | Medium | Done | Toan Le Tran | Done | Task | 3h
Toan Le Tran | Mock setup gitlab CI/CD with testing method |  | PSP2-22 | PSP2-10 | _ | Dec 15, 2023, 9:30 AM | Toan Le Tran | ci/cd | Medium | Done | Toan Le Tran | Done | Task | 3h
Sviatoslav Vasev | Discuss API integration with P4 group |  | PSP2-21 | PSP2-10 | _ | Oct 6, 2023, 2:00 PM | Sviatoslav Vasev | _ | Medium | Done | Sviatoslav Vasev | Done | Task | 15m
Anmol Arora | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Sep 27, 2023, 1:40 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 2h
Sviatoslav Vasev | Sprint Planning meeting time log | Standup meeting | PSP2-18 | PSP2-8 | _ | Sep 27, 2023, 11:00 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Sprint Planning meeting time log | Wednesday Sprint planning | PSP2-18 | PSP2-8 | _ | Oct 4, 2023, 11:12 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sviatoslav Vasev | Sprint Planning meeting time log | Sprint planning | PSP2-18 | PSP2-8 | _ | Oct 4, 2023, 11:00 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Oct 6, 2023, 12:41 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 2h
Sudikshya Bhattarai | Sprint Planning meeting time log | Sprint Planning | PSP2-18 | PSP2-8 | _ | Oct 6, 2023, 2:46 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sviatoslav Vasev | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Oct 6, 2023, 3:00 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h 30m
Sviatoslav Vasev | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Oct 13, 2023, 2:30 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h 30m
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 3, 2023, 11:16 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 20m
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 3, 2023, 2:24 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 3, 2023, 2:29 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sviatoslav Vasev | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 3, 2023, 2:30 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Sprint Planning meeting time log | 3/11 Friday meeting | PSP2-18 | PSP2-8 | _ | Nov 3, 2023, 2:43 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sviatoslav Vasev | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 8, 2023, 11:00 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Sprint Planning meeting time log | wednesday sprint 4 meeting | PSP2-18 | PSP2-8 | _ | Nov 17, 2023, 12:13 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 17, 2023, 2:51 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 17, 2023, 3:24 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Sprint Planning meeting time log | weekly sprint 4 | PSP2-18 | PSP2-8 | _ | Nov 22, 2023, 10:49 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 24, 2023, 7:44 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 24, 2023, 2:18 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 24, 2023, 1:49 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h
Jennifer Hensley | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Nov 29, 2023, 10:31 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Dec 8, 2023, 11:07 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Dec 8, 2023, 2:43 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Anmol Arora | Sprint Planning meeting time log | Sprint 6 weekly | PSP2-18 | PSP2-8 | _ | Dec 13, 2023, 10:40 AM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Dec 13, 2023, 10:49 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Dec 13, 2023, 10:49 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 30m
Sudikshya Bhattarai | Sprint Planning meeting time log |  | PSP2-18 | PSP2-8 | _ | Dec 13, 2023, 10:19 PM | Anmol Arora | _ | Medium | _ | Anmol Arora | In Progress | Task | 1h
Jennifer Hensley | Project roles definition |  | PSP2-17 | PSP2-1 | _ | Nov 3, 2023, 2:35 PM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 20m
Jennifer Hensley | Meeting notes to confluence |  | PSP2-15 | PSP2-1 | _ | Oct 4, 2023, 11:02 AM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 15m
Jennifer Hensley | Meeting notes to confluence |  | PSP2-15 | PSP2-1 | _ | Oct 4, 2023, 11:16 AM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 15m
Jennifer Hensley | Meeting notes to confluence |  | PSP2-15 | PSP2-1 | _ | Oct 6, 2023, 10:18 AM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 15m
Sudikshya Bhattarai | User needs and specifications in confluence |  | PSP2-14 | PSP2-1 | _ | Oct 6, 2023, 1:42 PM | Sudikshya Bhattarai | _ | Medium | Done | Anmol Arora | Done | Task | 1h 30m
Sviatoslav Vasev | Work Log/TimeSheet |  | PSP2-13 | PSP2-1 | _ | Sep 26, 2023, 10:00 AM | Sviatoslav Vasev | _ | Medium | Done | Anmol Arora | Done | Task | 1h
Toan Le Tran | Discuss testing possibilities for scrapper and bot |  | PSP2-12 | PSP2-10 | _ | Sep 29, 2023, 3:36 PM | Toan Le Tran | _ | Medium | Done | Anmol Arora | Done | Task | 3h
Sudikshya Bhattarai | Confluence page work distribution |  | PSP2-11 | PSP2-1 | _ | Oct 6, 2023, 1:11 PM | Sudikshya Bhattarai | _ | Medium | Done | Anmol Arora | Done | Task | 2h
Sudikshya Bhattarai | Confluence page work distribution |  | PSP2-11 | PSP2-1 | _ | Dec 8, 2023, 1:42 PM | Sudikshya Bhattarai | _ | Medium | Done | Anmol Arora | Done | Task | 1h 30m
Ozan Topcu | Database for storing job links and information |  | PSP2-9 | PSP2-10 | _ | Oct 27, 2023, 3:52 PM | Ozan Topcu | data | Medium | Done | Anmol Arora | Done | Task | 1h
Ozan Topcu | Database for storing job links and information |  | PSP2-9 | PSP2-10 | _ | Nov 3, 2023, 1:00 PM | Ozan Topcu | data | Medium | Done | Anmol Arora | Done | Task | 2h
Anmol Arora | Decide on period for storage of jobs and links |  | PSP2-7 | PSP2-10 | _ | Sep 25, 2023, 9:16 AM | Sviatoslav Vasev | _ | Medium | Done | Anmol Arora | Done | Task | 2h
Sviatoslav Vasev | Decide on period for storage of jobs and links |  | PSP2-7 | PSP2-10 | _ | Oct 4, 2023, 11:30 AM | Sviatoslav Vasev | _ | Medium | Done | Anmol Arora | Done | Task | 1h
Anmol Arora | Get a VM for scrapper or other alternatives can be disucssed | Pouta discussion | PSP2-6 | PSP2-10 | _ | Oct 11, 2023, 9:04 AM | Anmol Arora | vm | Medium | Done | Anmol Arora | Done | Task | 2h
Sviatoslav Vasev | Find API or decide on scrapper for jobs |  | PSP2-4 | PSP2-10 | _ | Oct 5, 2023, 9:30 AM | Sviatoslav Vasev | data | Medium | Done | Anmol Arora | Done | Task | 30m
Anmol Arora | Setup Confluence pages |  | PSP2-3 | PSP2-1 | _ | Sep 22, 2023, 1:55 PM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 2h
Jennifer Hensley | Setup Confluence pages |  | PSP2-3 | PSP2-1 | _ | Sep 27, 2023, 10:39 AM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 1h
Jennifer Hensley | Setup Confluence pages |  | PSP2-3 | PSP2-1 | _ | Sep 29, 2023, 3:57 PM | Jennifer Hensley | _ | Medium | Done | Anmol Arora | Done | Task | 30m
Sviatoslav Vasev | TB-DragonFly |  | PSP2-1 | _ | _ | Sep 22, 2023, 2:00 AM | Anmol Arora | _ | Medium | Done | Anmol Arora | Done | Epic | 3h
_ |  | _ | _ | _ | _ |  | _ | _ | _ | _ | _ | _ | _ | 163h 35m